## Sheet1
Task Name | Task Mode | Duration | Start Date | End Date | Predecessor
Project Brief | Done | 2 | 2015-03-22 | 2015-03-24
PID Initiation | Done | 4 | 2015-03-26 | 2015-03-30 | Project Brief
PID Finalising | On | 2 | 2015-04-07 | 2015-04-09 | PID Initiation
Messenger Execution | To Do | 1 | 2015-04-10 | 2015-04-11 | PID Finalising
Testing | To Do | 1 | 2015-04-11 | 2015-04-12 | Messenger Execution
Private Chat | To Do | 2 | 2015-04-12 | 2015-04-14 | Testing
Chat History | To Do | 4 | 2015-04-12 | 2015-04-16 | Testing
File Sharing | To Do | 5 | 2015-04-14 | 2015-04-19 | Testing
Centralized Database | Tentative-To Do | 1 | 2015-04-19 | 2015-04-20 | Private Chat, File Sharing, Chat History
Closeup | To Do | 1 | 2015-04-20 | 2015-04-21 | Centralized database
Exam Report | To Do | 9 | 2015-04-21 | 2015-04-30

## Sheet2
Risk ID | Risk Name | Description | Impact (I) | Frequency (F) | Risk Factor= I*F | Date Logged In | Person Responsible | Risk Mitigation Strategy
R1 | Abseentism | If the team member is ill or can't come | 4 | 2 | 8 |  | Developers | Incentives and warnings are established to encourage the responsibility and positive behavior while eliminating negative attitude towards work.
R2 | Technical | If one or more of the components of project are not working | 4 | 2 | 8 |  | QA Team | All products and components Tested before final Delivery
R4 | Project Bigger | If code is taking longer than expected | 3 | 2 | 6 |  | Developers | Work break down structure should be made and Daily sprint meetings to show the deliverables.
R3 | Member Leaving | If team member is being pulled out or leaving | 4 | 1 | 4 |  | Scrum Team | To avoid the risk work should be completed earlier than deadlines so in such case work should be covered by members till deadline.
R5 | Financial | No source available to meet cost | 4 | 1 | 4 |  | Accounts | Open source softwares are being used so the buildup cost is zero.
R6 | Stakeholder | Stakeholder Leaving | 4 | 1 | 4 |  | Project Manager | Very few chances of stakeholders leaving.
R7 | Sales | Product is not made for sale | 1 | 1 | 1 |  | Team | No risk